## Group Contribution Log
Course | CS3343
Term | 2024-25 Semester A
Project No. | 2
Project Name/Title | CityU Cinema System
No. of Team Members | 5
Project Manager Name | Chan Ka Hong
Student ID | Name (Last, First) | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Total | Student | Relative | Contribution | e.g.Group Mark | Final Adjusted
57845658 | CHAN, Ka Hong | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 1300 | CHAN, Ka Hong | 1 | 100% | 80 | 80
56755919 | FUNG, Wing Ho | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 1300 | FUNG, Wing Ho | 1 | 100% | 80 | 80
57847086 | WONG, Tsz Kin | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 1300 | WONG, Tsz Kin | 1 | 100% | 80 | 80
56652261 | NG, Ka Ho | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 1300 | NG, Ka Ho | 1 | 100% | 80 | 80
57842515 | LAW, Lok Hang | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 1300 | LAW, Lok Hang | 1 | 100% | 80 | 80
| Total Effort | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 6500 | Max | 1 |  | Average | 80
[19 empty] | Max | 80
[19 empty] | Min | 80

## Weekly Activity Log
Week | Weekly Activity Log | Completed By
Week 1 | Recruited memebers to form a project team. In the end, we have 5 members in the team. | Chan Ka Hong
Week 2 | We had our first meeting where we discussed the possible project ideas that were feasible to work on. We preliminarily settled on making a movie ticketing and management system that supports some common functions such as allowing customers to select movies and book tickets and letting system admin to schedule movies. | The whole team
Week 3 | We had our second meeting to discuss some more details of the system. For example, we thought about how the system accepts user inputs e.g. commands or input one by one based on prompts; we talked about if the system should save any data. We also decided each of our roles for the project. | The whole team
Week 4 | We had our third meeting where we finalized on the key functions that would be included in the system. We distributed our work based on the functions and we started working on the design and writing codes for the system. | The whole team
Week 5 | We set some internal deadlines to make sure the project could go smoothly and complete as anticipated. We began to write codes for our respective sections of the system and did some unit testings. Some early finished codes were pushed to Github. | The whole team
Week 6 | We continued to finish up, debug, refactor, and write test cases for the codes within the modules required for the first integration. We documented the bugs and tests in our report. | The whole team
Week 7 | We finalized and finished up the remaining codes in preparation for the first integration. Unit testing and debugging took place in the meantime. | The whole team
Week 8 | We had our first integration of the early completed modules. Integration test cases were written and documented. We released our first executable jar file which served as a prototype for proof-of-concept. | The whole team
Week 9 | We kickstarted the development of the remaining modules such as payment, user, I/O, etc. Unit testing, debugging, and refactoring were simultaneously performed during development. | The whole team
Week 10 | We finalized and finished up the remaining codes in preparation for the second integration. Unit testing, debugging, and refactoring continued as usual. | The whole team
Week 11 | We had our second integration for the remaining modules completed in the previous weeks. More integration test cases were written and documented. We released our second executable jar file, which was also the final version of our program. | The whole team
Week 12 | We continued to work on any unfinnished sections of documentation and report. | The whole team
Week 13 | We finalized report content, prepared content for project delivery and presentation, and rehersed for the final presentation. | The whole team